## MoM Summary
Sr. No. | Meeting Date | Meeting Mode | Meeting Location | Agenda | Contact Details |  |  |  |  | Key Discussion Point | Key Actionable
[5 empty] | Person Name | Designation & Department | Contact Number | Email Id | EY Team
1 | 2018-06-22 | Physical meeting | Mela Office | Discussion on scope with regards to development of website and mobile app, work plan and gathering of relevant content | Mr. Vijay Kumar Anand | Mela Adhikari | +91 94120 50016 |  | Mr. Ashish Verma Mr. Manish Jakhmola Mr. Sagar Bele Mr. Swapnil Kumar Mr. Manish Singh | 1. Primary purpose of website and mobile app is to provide information to citizens with regards to various initiatives taken by the Government so that they are not facing any problem during their visit to Mela 2. There shall not be any transaction 3. EY team to meet different stakeholders to initiate content gathering 4. EY team presented the revised sitemap and further feedback was provided | 1. Meet different stakeholders to initiate content gathering for website and mobile application 2. Sitemap to be revised
2 | 2018-06-23 | Physical meeting | Department of Tourism, Allahabad | 1. Receive contents for events arranged/managed by Tourism Department 2. Receive contents for Travel related details | Mr. Anupam Srivastava | Regional Tourism Officer | +91 99531 22008 | rtold0532@rediffmail.com | Mr. Ashish Verma Mr. Manish Jakhmola Mr. Sagar Bele Mr. Swapnil Kumar | 1. Department to provide information with regards to empaneled hotels and PGs and same shall be made available 2. Information with regards to various events managed by department to be made available like Thematic gates, tourist walk, lazor light show, etc. 3. System should have provision to upload photos and videos against all such events on regular basis | 1. List of required content to be shared with Department 2. Department to provide all the content in soft copy
3 | 2018-06-23 | Telecon | Telecon | 1. Receive contents for Rituals of Kumbh, Astrological Significance, Mythological Significance, Spiritual Gurus | Mr. Vachaspati Tripathi |  |  |  | Mr. Ashish Verma Mr. Manish Jakhmola Mr. Sagar Bele Mr. Swapnil Kumar | 1. Mr. Vachaspati to provide information with regards to Rituals of Kumbh, Astrological Significance, Mythological Significance, Spiritual Gurus events on regular basis | 1. Mr. Vachaspati to provide all the content in soft copy
4 | 2018-06-24 | Physical meeting | Police Department | 1. Collect contents for services provided by Police department | Mr. Kavider Singh | Police Department |  |  | Mr. Ashish Verma Mr. Manish Jakhmola Mr. Sagar Bele Mr. Swapnil Kumar | 1. In Mobile app, current location of the user should be displayed while aceesing location based search 2. Department to provide details of all the content to be made available, like Security Services, Traffic Plan, Emergency Services, Disaster Management, Lost & Found 3. Department shall made available a dedicated team during Kumbh to faciliate timely availability of the verified information | 1. Contents to be provided by Police department

## Content Summary
Sr. No. | Meeting ID | Meeting Date | Meeting Location | Page (Site Map Heading) | Approving Client Team |  |  |  | EY Team | 3rd Party Vendor Team |  |  |  | Content Requested on | Content Format (Soft Copy - Audio/ Video/ Text/ Document; Hard Copy) | Content Type (English/Hindi) | Content Location | Content Provided By |  | Content Updating Frequency | Status | Actionable | Remark
[5 empty] | Name | Designation & Department | Contact Number | Email |  | Name | Designation & Company | Contact Number | Email |  |  |  |  | Name | Contact Number
1 | 2 | 2018-06-23 | Department of Tourism, Allahabad | Mela Attraction | Mr. Anupam Shrivastava | Regional Tourism Officer | 9953122008 | rtold0532@rediffmail.com | Mr. Ashish Verma Mr. Manish Jakhmola Mr. Sagar Bele Mr. Swapnil Sharma | NA | NA | NA | NA | Thematic Gates |  |  |  | Mr. Anupam Shrivastava | 9953122008 | Static | Not Received | 1. Visit UP tourism website (http://uptourism.gov.in/) 2. All available contents to be provided by Tourism department in soft/hard copy format
2 | 2 | 2018-06-23 | Department of Tourism, Allahabad | Mela Attraction | Mr. Anupam Shrivastava | Regional Tourism Officer | 9953122008 | rtold0532@rediffmail.com | Mr. Ashish Verma Mr. Manish Jakhmola Mr. Sagar Bele Mr. Swapnil Sharma | NA | NA | NA | NA | Tourist walk |  |  |  | Mr. Anupam Shrivastava | 9953122008 | Static | Not Received | 1. Visit UP tourism website (http://uptourism.gov.in/) 2. All available contents to be provided by Tourism department in soft/hard copy format
3 | 2 | 2018-06-23 | Department of Tourism, Allahabad | Mela Attraction | Mr. Anupam Shrivastava | Regional Tourism Officer | 9953122008 | rtold0532@rediffmail.com | Mr. Ashish Verma Mr. Manish Jakhmola Mr. Sagar Bele Mr. Swapnil Sharma | NA | NA | NA | NA | Laser Light Show |  |  |  | Mr. Anupam Shrivastava | 9953122008 | Static | Not Received | 1. Visit UP tourism website (http://uptourism.gov.in/) 2. All available contents to be provided by Tourism department in soft/hard copy format
4 |  |  |  | About Kumbh |  | Mela Adhikari | [7 empty] | Kumbh Introduction |  |  |  | EY PMU Team |  | Static | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
5 |  |  |  | About Kumbh |  | Mela Adhikari | [7 empty] | Rituals of Kumbh |  |  |  | Mr. Vasapati Tripathi |  | Static | Not Received | 1. To be provided by Mr. Vasapati Tripathi 2. Proof Reading and Consolidation of content by PMU team 3. Approval by Mela Adhikari
6 |  |  |  | About Kumbh |  | Mela Adhikari | [7 empty] | Astrological Significance |  |  |  | Mr. Vasapati Tripathi |  | Static | Not Received | 1. To be provided by Mr. Vasapati Tripathi 2. Proof Reading and Consolidation of content by PMU team 3. Approval by Mela Adhikari
7 |  |  |  | About Kumbh |  | Mela Adhikari | [7 empty] | Mythological Significance |  |  |  | Mr. Vasapati Tripathi |  | Static | Not Received | 1. To be provided by Mr. Vasapati Tripathi 2. Proof Reading and Consolidation of content by PMU team 3. Approval by Mela Adhikari
8 |  |  |  | About Kumbh |  | Mela Adhikari | [7 empty] | Spiritual Gurus |  |  |  | Mr. Vasapati Tripathi |  | Static | Not Received | 1. To be provided by Mr. Vasapati Tripathi 2. Proof Reading and Consolidation of content by PMU team 3. Approval by Mela Adhikari
9 |  |  |  | About Kumbh |  | Mela Adhikari | [7 empty] | Research on Kumbh |  |  |  | EY PMU Team |  | Static | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
10 |  |  |  | About Allahabad |  | Mela Adhikari | [7 empty] | History |  |  |  | EY PMU Team |  | Static | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
11 |  |  |  | About Allahabad |  | Mela Adhikari | [7 empty] | About Sangam |  |  |  | EY PMU Team |  | Static | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
12 |  |  |  | About Allahabad |  | Regional Tourism Officer |  |  | Mr. Ashish Verma Mr. Manish Jakhmola Mr. Sagar Bele Mr. Swapnil Sharma | NA | NA | NA | NA | Temples of Allahabad | Word Document - Email | English | \Kumbh\Website\About Allahabad\Tourist Attractions\ListofAttraction_2018-06-24_v1.docx | Mr. Anupam Shrivastava | 9953122008 | Static | Partial Data Received | 1. Added in website 2. Data received to be added on provided for approval to Mela Adhikari | 1. Partial Data Received on places in Allahabad
13 |  |  |  | About Allahabad |  | Regional Tourism Officer |  |  | Mr. Ashish Verma Mr. Manish Jakhmola Mr. Sagar Bele Mr. Swapnil Sharma | NA | NA | NA | NA | Tourist Attractions | Word Document - Email | English | \Kumbh\Website\About Allahabad\Tourist Attractions\ListofAttraction_2018-06-24_v1.docx | Mr. Anupam Shrivastava | 9953122008 | Static | Partial Data Received | 1. Added in website 2. Data received to be added on provided for approval to Mela Adhikari | 1. Partial Data Received on places in Allahabad
14 |  |  |  | About Allahabad |  | Mela Adhikari | [7 empty] | Major Festivals and Events |  |  |  | EY PMU Team |  | Dynamic | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
15 |  |  |  | About Allahabad |  | Mela Adhikari | [7 empty] | Food |  |  |  | EY PMU Team |  | Dynamic | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
16 |  |  |  | About Allahabad |  | Regional Tourism Officer | [7 empty] | Nearby Places to Visit |  |  |  | Mr. Anupam Shrivastava | 9953122008 | Static | Not Received | 1. Visit UP tourism website (http://uptourism.gov.in/) 2. All available contents to be provided by Tourism department in soft/hard copy format
17 |  |  |  | Kumbh 2019 |  | Mela Adhikari | [7 empty] | Highlights |  |  |  | EY PMU Team |  | Dynamic | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
18 |  |  |  | Kumbh 2019 |  | Mela Adhikari | [7 empty] | Holy Dip Dates |  |  |  | EY PMU Team |  | Dynamic | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
19 |  |  |  | Kumbh 2019 |  | Mela Adhikari | [7 empty] | Infrastructure Details |  |  |  | EY PMU Team |  | Dynamic | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
20 |  |  |  | Kumbh 2019 |  | Mela Adhikari | [7 empty] | Do’s and Don’ts |  |  |  | Police Department |  | Static | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
21 |  |  |  | Events Calendar |  | Mela Adhikari | [7 empty] | Holy Dip Dates |  |  |  | EY PMU Team |  | Dynamic | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
22 |  |  |  | Events Calendar |  | Mela Adhikari | [7 empty] | Cultural Events Calendar |  |  |  | EY PMU Team |  | Dynamic | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
23 |  |  |  | Travel and Stay |  | NA | [7 empty] | Weather |  |  |  | EY Development Team |  | Dynamic | Not Received | It will be part of development
24 |  |  |  | Travel and Stay |  | NA | [7 empty] | Allahabad Map |  |  |  | EY PMU Team |  | Static | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
25 |  |  |  | Travel and Stay | Mr. Anupam Shrivastava | Regional Tourism Officer | 9953122008 | rtold0532@rediffmail.com | [5 empty] | How to Reach |  |  |  | Mr. Anupam Shrivastava | 9953122008 | Dynamic | Not Received | 1. Visit UP tourism website (http://uptourism.gov.in/) 2. All available contents to be provided by Tourism department in soft/hard copy format
26 |  |  |  | Travel and Stay | Mr. Anupam Shrivastava | Regional Tourism Officer | 9953122008 | rtold0532@rediffmail.com | [5 empty] | Where to Stay |  |  |  | Mr. Anupam Shrivastava | 9953122008 | Dynamic | Not Received | 1. Visit UP tourism website (http://uptourism.gov.in/) 2. All available contents to be provided by Tourism department in soft/hard copy format
27 |  |  |  | Citizen Corner |  | Mela Adhikari | [7 empty] | Youths for Kumbh Campaign |  |  |  | EY PMU Team |  | Dynamic | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
28 |  |  |  | Mela Attraction |  | Mela Adhikari | [7 empty] | Paint My City |  |  |  | EY PMU Team |  | Dynamic | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
29 |  |  |  | Citizen Corner |  | Mela Adhikari | [7 empty] | Merchandise |  |  |  | EY PMU Team |  | Dynamic | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
30 |  |  |  | Citizen Corner |  | Mela Adhikari | [7 empty] | Testimonials |  |  |  | EY PMU Team |  | Dynamic | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
31 |  |  |  | Social Media |  | Mela Adhikari | [7 empty] | Social Media |  |  |  | EY PMU Team |  | Dynamic | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
32 |  |  |  | Gallery |  | Mela Adhikari | [7 empty] | Photo |  |  |  | EY PMU Team |  | Dynamic | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
33 |  |  |  | Gallery |  | Mela Adhikari | [7 empty] | Video |  |  |  | EY PMU Team |  | Dynamic | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
34 |  |  |  | Gallery |  | Mela Adhikari | [7 empty] | Downloads |  |  |  | EY PMU Team |  | Dynamic | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
35 |  |  |  | Help Desk |  | Mela Adhikari | [7 empty] | Security Services |  |  |  | Police Department |  | Dynamic | Not Received | 1. Contents to be provided by Police department
36 |  |  |  | Help Desk |  | Mela Adhikari | [7 empty] | Traffic Plan |  |  |  | Police Department |  | Dynamic | Not Received | 1. Contents to be provided by Police department
37 |  |  |  | Help Desk |  | Mela Adhikari | [7 empty] | Emergency Services |  |  |  | Police Department |  | Dynamic | Not Received | 1. Contents to be provided by Police department
38 |  |  |  | Help Desk |  | Mela Adhikari | [7 empty] | Disaster Management |  |  |  | Police Department |  | Static | Not Received | 1. Contents to be provided by Police department
39 |  |  |  | Help Desk |  | Mela Adhikari | [7 empty] | Lost & Found |  |  |  | Police Department |  | Dynamic | Not Received | 1. Contents to be provided by Police department
40 |  |  |  | Contacts |  | Mela Adhikari | [7 empty] | Mela Administration |  |  |  | Mela Adhikari |  | Dynamic | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
41 |  |  |  | Contacts |  | Mela Adhikari | [7 empty] | Departments |  |  |  | Mela Adhikari |  | Static | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
42 |  |  |  | Contacts |  | Mela Adhikari | [7 empty] | Emergency Contacts |  |  |  | Mela Adhikari |  | Static | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
43 |  |  |  | Blogs |  | Mela Adhikari | [7 empty] | Blogs |  |  |  | Mela Adhikari |  | Dynamic | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
44 |  |  |  | FAQs |  | Mela Adhikari | [7 empty] | FAQs |  |  |  | Mela Adhikari |  | Static | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
45 |  |  |  | Important Links |  | Mela Adhikari | [7 empty] | Indian embassies |  |  |  | Mela Adhikari |  | Static | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
46 |  |  |  | Important Links |  | Mela Adhikari | [7 empty] | Airlines |  |  |  | Mela Adhikari |  | Static | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
47 |  |  |  | Important Links |  | Mela Adhikari | [7 empty] | Railways |  |  |  | Mela Adhikari |  | Static | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
48 |  |  |  | Important Links |  | Mela Adhikari | [7 empty] | Bus Services |  |  |  | Mela Adhikari |  | Static | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
49 |  |  |  | Important Links |  | Mela Adhikari | [7 empty] | Tourism offices |  |  |  | Mela Adhikari |  | Static | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
50 |  |  |  | Important Links |  | Mela Adhikari | [7 empty] | Government portals |  |  |  | Mela Adhikari |  | Static | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
51 |  |  |  | Home Page |  | Mela Adhikari | [7 empty] | Home Page |  |  |  | Mela Adhikari |  | Dynamic | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari
52 |  |  |  | Location Finder |  | Mela Adhikari | [7 empty] | Location Finder |  |  |  | Mela Adhikari |  | Dynamic | Not Received | 1. To be provided by PMU Team 2. Approval by Mela Adhikari